## Result
WELD INSPECTION REPORT
Visual & NDT Examination Log — per EN ISO 5817 / AWS D1.1
Report No. WIR-2026-0418
Page 1 of 1
Project
Location
Date
Pipe Rack Module B-12
Bay 4, Workshop
14 Apr 2026
Client
Inspector
Standard
NorthSteel Fabrication
D. Weld, CSWIP 3.1
EN ISO 5817 Level B
WELD INSPECTION REPORT
Joint No. | WPS No. | Welder ID | Process | Material | Tbk (mm) | Position | NDT | Defect | Result
J-101 | WPS-014 | W-207 | GTAW | 316L | 6.0 | 2G | VT+PT | None | ACC
J-102 | WPS-014 | W-207 | GTAW | 316L | 6.0 | 6G | RT | Porosity | REJ
J-103 | WPS-022 | W-115 | SMAW | S355 | 12.0 | 3G | VT+MT | None | ACC
J-104 | WPS-022 | W-115 | SMAW | S355 | 12.0 | 4G | UT | Undercut | REJ
J-105 | WPS-031 | W-340 | FCAW | S275 | 10.0 | 1G | VT | None | ACC
J-106 | WPS-031 | W-340 | FCAW | S275 | 10.0 | 2F | VT+MT | None | ACC
J-107 | WPS-014 | W-207 | GTAW | 316L | 4.0 | 5G | RT | Lack of fusion | REJ
J-108 | WPS-045 | W-118 | GMAW | S355 | 8.0 | 2G | VT+PT | None | ACC
J-109 | WPS-045 | W-118 | GMAW | S355 | 8.0 | 3G | UT | None | ACC
J-110 | WPS-022 | W-115 | SMAW | S355 | 12.0 | 4G | VT | Spatter | ACC
J-111 | WPS-031 | W-340 | FCAW | S275 | 10.0 | 1G | RT | Slag incl. | REJ
J-112 | WPS-014 | W-207 | GTAW | 316L | 6.0 | 6G | VT+PT | None | ACC
WELD INSPECTION REPORT
Total joints | 12 · Accepted: 8 · Rejected: 4 · Repair rate: 33%
Inspector signature
QA/QC Manager